## Project Data
Project | AIlixir Patient Journey Matcher
Online team meeting | https://fau.zoom-x.de/j/63814190741?pwd=IqXz0xbIrMCk01I1RENueDyarj9E34.1
Production system (if any) | ...
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2026ws03-patient-journey-matcher
GitHub feature board | https://github.com/orgs/amosproj/projects/111
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/115
Position of T-shirt logo | Upper Torso Right Small
Link to logo for black T-shirt | https://github.com/amosproj/amos2026ws03-patient-journey-matcher/blob/main/Deliverables/sprint-01/team-logo.png
Link to logo for white T-shirt | https://github.com/amosproj/amos2026ws03-patient-journey-matcher/blob/main/Deliverables/sprint-01/team-logo.png
Additional materials | ...
Team mailing list | oss-amos-proj3@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Richter | Miriam | miri-ri | miriam.richter@campus.tu-berlin.de
Meligy | Ziad | ZiadMeligy | ziad.meligy.abdelghany@fau.de
Tasken | Eren | erentasken | eren.tasken@fau.de
Neubauer | Robin | robin38n | robin.neubauer@fau.de
Zink | Nina | nizi0015 | nina-sophie.zink@fau.de
Cekic | Erman | ermancekic | erman.cekic@fau.de
Pfahlmann | Fabian | Chronuak | fabian.jannik.pfahlmann@fau.de
Reinel | Moritz | moritz-reinel | mo.ritz@fau.de
Adas | Munir | Munirad7s | munir.adas@fau.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2026-10-14 |  | Fabian Pfahlmann | Everyone else | N/A | Moritz Reinel
2 | 2026-10-21 | Fabian Pfahlmann | Miriam Richter | Everyone else | Robin Neubauer | Moritz Reinel
3 | 2026-10-28 | Miriam Richter | Fabian Pfahlmann | Everyone else | Ziad Meligy | Moritz Reinel
4 | 2026-11-04 | Fabian Pfahlmann | Miriam Richter | Everyone else | Eren Tasken | Moritz Reinel | Build process review
5 | 2026-11-11 | Miriam Richter | Fabian Pfahlmann | Everyone else | Nina Zink | Moritz Reinel
6 | 2026-11-18 | Fabian Pfahlmann | Miriam Richter | Everyone else | Ziad Meligy | Moritz Reinel
7 | 2026-11-25 | Miriam Richter | Fabian Pfahlmann | Everyone else | Munir | Moritz Reinel | Mid-term due
8 | 2026-12-02 | Fabian Pfahlmann | Miriam Richter | Everyone else | Munir | Moritz Reinel
9 | 2026-12-09 | Miriam Richter | Fabian Pfahlmann | Everyone else | Robin Neubauer | Moritz Reinel
10 | 2026-12-16 | Fabian Pfahlmann | Miriam Richter | Everyone else | Nina Zink | Moritz Reinel
11 | 2027-01-13 | Miriam Richter | Fabian Pfahlmann | Everyone else | Erman cekic | Moritz Reinel
12 | 2027-01-20 | Fabian Pfahlmann | Miriam Richter | Everyone else | Erman cekic | Moritz Reinel
13 | 2027-01-27 | Miriam Richter | Fabian Pfahlmann | Everyone else | Ziad Meligy | Moritz Reinel
14 | 2027-02-03 | Fabian Pfahlmann | Miriam Richter | Everyone else |  | Moritz Reinel | Demo day!
15 | 2027-02-10 | Miriam Richter |  | Everyone else |  | Moritz Reinel | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here

## Team Contract
Goals | The team aims to meet all of the teaching team's requirements, meet all deadlines on time, and deliver a high-quality open-source MCP server that provides tangible added value for AIlixir.
Every team member will actively expand their technical or organizational skills while fostering a supportive and psychologically safe working environment.
Meeting norms | Team members shall arrive on time for all scheduled meetings.
Team members shall keep their video cameras turned on during online meetings to facilitate engaged, face-to-face collaboration.
In case of unavoidable absence, members will inform the team on Slack and notify the team and teaching team via email as early as possible.
Working norms | High-quality code documentation should be provided, including graphical documentation and, for example, UML diagrams.
For the purpose of repository hygiene, there should be separate feature branches, and at least one reviewer (depending on the number of authors or the scope of the feature) for each feature merge. Direct pushing or force-pushing to the main branch is strictly prohibited, and all pull requests require at least one peer approval and must pass CI checks.
Team members may use AI assistance, but every author shall be capable of explaining their committed code line-by-line ("No AI slop").
Coordination norms | Team members shall distribute tasks fairly and transparently across the team during sprint planning.
Team members shall continuously update the status of their work items on the GitHub Project Board to maintain visibility
Communication norms | Asynchronous communication will take place on Slack. Members shall communicate their availability during the sprint in advance.
Members shall respond to Slack messages within 12–24 hours on working days (same-day response), and faster leading up to major project deadlines.
Consideration norms | Team members shall provide constructive and polite feedback during code reviews and respect diverse opinions.
Members shall communicate mistakes early and transparently without fear of judgment.
Cont. improvement norms | The team shall actively participate in sprint retrospectives, providing honest input to improve team processes.
Team members shall maintain clean inline code documentation and graphical/UML diagrams to ensure continuous knowledge sharing.
Rewards | Upon successfully completing milestones, the team will celebrate together with a shared team drink (virtually or in person).
Sanctions | Unexcused tardiness to meetings or unannounced missed deadlines shall be sanctioned with 5 to 20 jumping jacks (scaled by delay) at the start of the next team meeting.
Signatures
Scrum Master | Moritz Reinel
Product owner | Fabian Pfahlmann
Product owner | Miriam Richter
Software developer | Mohamad Munir Adas
Software developer | Ziad Meligy
Software developer | Erman Cekic
Software developer | Eren Tasken
Software developer | Robin Neubauer
Software developer | Nina Zink

## Product Goal
Product Vision | Project Mission
An open-source, AI-enabled healthcare integration layer that matches personal health journeys with relevant, qualitative medical insights, helping patients better understand, track and navigate their individual condition. | To design and implement a Model Context Protocol (MCP) server for the mobile AIlixir application that matches synthetic patient journeys with qualitative sources (PubMed, podcasts, literature) using keyword, graph, and LLM-based summarization to deliver clear information back to the patient.

## Product Glossary
Term | Definition

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Optional
5 | Write your sprint goal here
6
7
8
9
10
11
12
13
14
15

## Velocity Tracking
Sprint # | Story Points Realized
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done

## Documentation
Type | Link / reference

## Bill of Materials
# | Context | Name | Version | License | Comment

## Planning Poker
Last Name | First Name | Value
Reinel | Moritz | 0 | 0 | OK
Richter | Miriam | 0
Meligy | Ziad
Neubauer | Robin
Zink | Nina |  | 0 | No size
Cekic | Erman |  | 1 | Trivial size
Pfahlmann | Fabian |  | 2 | Small size
Tasken | Eren |  | 3 | Medium size
Adas | Munir |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value